## Slide 1
R
A
G
Project Health Report
Week ending 2026-07-10
For Client Leadership Review

## Slide 2
Portfolio RAG Dashboard
3
Total Projects
2
Red
1
Amber
0
Green
Red
2
Amber
1
Green
0
Project Detail
Red
Zycus - UniSan S2P Implementation
44% · Rajat Bothra
Amber
CRM Migration
70% · N/A
Red
Zycus - Titan S2P Implementation
71% · Aftab Hashambhai

## Slide 3
Project Detail & Signal Breakdown
Zycus - UniSan S2P Implementation
Red
44% complete
schedule slippage
Amber
budget burn
—
milestone health
Red
blockers
Red
stakeholder sentiment
—
PM: Rajat Bothra
CRM Migration
Amber
70% complete
schedule slippage
—
budget burn
Red
milestone health
Green
blockers
Green
stakeholder sentiment
—
PM: N/A
Zycus - Titan S2P Implementation
Red
71% complete
schedule slippage
Amber
budget burn
—
milestone health
Red
blockers
Green
stakeholder sentiment
—
PM: Aftab Hashambhai

## Slide 4
Trend Analysis
Current snapshot — trends will appear after 2+ weeks of data collection.
Project
Status
Schedule
Milestones
Blockers
Zycus - UniSan S2P Implementation
Red
● Amber
● Red
● Red
CRM Migration
Amber
○ —
● Green
● Green
Zycus - Titan S2P Implementation
Red
● Amber
● Red
● Green

## Slide 5
Emerging Risks
Critical
Zycus - UniSan S2P Implementation
Multiple Red signals — schedule slippage and overdue milestones. Escalation recommended.
High
Zycus - UniSan S2P Implementation
Overdue milestone tasks indicate delivery timeline risk.
Watch
CRM Migration
Budget overrun or signal drift. Requires active monitoring and mitigation plan.
Critical
Zycus - Titan S2P Implementation
Multiple Red signals — schedule slippage and overdue milestones. Escalation recommended.
High
Zycus - Titan S2P Implementation
Overdue milestone tasks indicate delivery timeline risk.

## Slide 6
Insights & Recommendations
!
3 of 3 projects require attention
2 Red (immediate escalation) and 1 Amber (monitoring) status projects identified.
D
Data gaps limit assessment depth
Budget and stakeholder sentiment fields are missing from standard exports. Adding these would improve accuracy.
M
Milestone overdue is the top risk driver
Across all projects, overdue tasks are the primary factor pushing status to Red.
R
Recommend adding structured sentiment field
A PM status-comment field would enable the sentiment signal and provide richer context.

## Slide 7
Methodology
Project Health Reporting Agent | RAG_METHODOLOGY.md
Schedule
% of tasks flagged Red determines status (≤5% Green, ≤15% Amber, >15% Red)
Budget
Burn ratio = spend% / complete%. Compares spending rate against progress rate.
Milestones
Count of overdue (past End Date) incomplete tasks. >15 = Red, 6-15 = Amber.
Blockers
Overdue critical tasks serve as blocker proxy. >2 = Red, 1-2 = Amber.
Sentiment
Narrative signal from PM comments. Currently disabled — no structured source field.
Overall status = worst signal, except single-Red capped to Amber if all other signals are Green. | Thresholds: config/rag_thresholds.yaml